### Case Study Plan

2003/01/31

Version: 1.0

Updated History

| Date | Description | Who |
| --- | --- | --- |
| 2003/01/31 | Created | Judy |

# Purpose

The business goal of organizational process improvement is: improve product quality and achieve CMM level 2 within 12 months.  Through this case study, we would like to understand our SPI work progress and achievements, and evaluate the benefit of SPI and progress of achieving the business goals, and finally summarize the lessons learnt preventing from future work.

# Scope

In this case study, it summarizes our current (2002/05-2002/12) SPI work at requirement management, quality management and project manager capability within software development department.

# Roles & Responsibility

| Role | Example | Responsibility |
| --- | --- | --- |
| Project Leader | SEPG Leader | Develop the plan, be responsible for management work, cooperate with support people, and report the results to senior manger |
| Team Member | SEPG Member | Collect information from projects, analyze and consolidate information, and write case study |
| Support | Project Managers项目经理 | Provide project’s detailed information |
|  | Senior Managers, PIA | Provide suggestion and instruction on case study development |

# Risks

| No. | Description | Possibility | Impact | Solution |
| --- | --- | --- | --- | --- |
| 1 | Not enough resources | Middle | Middle | Negotiate with related managers to get enough resources |
| 2 | Information collection requires much effort | High | Middle | Develop a tool to support collecting information |
| 3 | Collected information may not show the expected improvement results | Low | Big | Analyze the correctness and integrity of data, and adjust the method for data collection |
| 4 | First time to write case study, the result might not be as good as expected | Low | Big | Accept professional training course |

# Schedule

  - In table

| No. | Task name | Start Date | End Date | Status |
| --- | --- | --- | --- | --- |
| 1. | Identify Issues | 12/27/02 | 12/27/02 |  |
| 2. | Issues 1 | 12/30/02 | 1/2/03 |  |
| 2.1 | Identify improvement approach | 12/30/02 | 12/30/02 |  |
| 2.2 | Information collection | 12/31/02 | 12/31/02 |  |
| 2.3 | Information analysis | 1/2/03 | 1/2/03 |  |
| 3. | Information consolidation | 1/3/03 | 1/3/03 |  |
| 4. | Write case study | 1/4/03 | 1/5/03 |  |
| 5. | Review case study | 1/6/03 | 1/6/03 |  |
| 6. | Publish case study | 1/7/03 | 1/9/03 |  |

Notes: Not started, In-progress, Done

  - MS Project：

Case Study Plan.mpp

# Others

  - Training Plan

| Date | Content | Duration | Method | Participants |
| --- | --- | --- | --- | --- |
| 2003/02/01 | Case Study Workshop | 1day | PIA | All SEPG members, and invited project leaders |
| 2003/02/14 | Measuring Software Process | 3days | PIA | All SEPG members, middle managers and invited project leaders |